Swanzey Strategic Review — Two-Page Summary

Restraint and Its Limits · Prepared for the Board of Selectmen · PublicLogic VAULT · v0.1 · June 2026

The argument: Swanzey leads with restraint. It built a decade of voter trust — and, used the same way again, it will starve the Town's capital and erode that trust. Don't abandon restraint; upgrade the instrument: save first, leverage outside money, tell residents the plain truth.

A.  By the numbers (2012–2026)

| Metric | Where it stands | What it means |
| --- | --- | --- |
| Operating budget | $5.75M → $8.94M (+55%) | Now +6–7%/yr — health, wages, retirement, ambulance; not new programs |
| Budget voter support | ~81% → 57% | Trust eroding even though taxes were held |
| Reserves & tax credits | pass 78–90% | The town will SAVE |
| Facility bonds (need 3/5) | 55–58% — failed 2024 & 2026 | The town won't BORROW; a majority isn't enough at the 3/5 wall |
| Default vs. proposed budget | within $47K (2026) | 'Vote no to save' no longer works; in 2017/18/23 the default was higher |
| Total tax rate | $24.51 (2021) → $20.18 (2025) | 2024 drop was a revaluation, not a cut; ~60% of the bill is school/county |
| Town administrators | 3 in ~2 years | Continuity is the scarcest resource |
| New obligation | West Swanzey water (2025) | A multi-million utility now on the books |

B.  The pattern — confidence up, capacity down

| The consistent choice | Evidence | Effect |
| --- | --- | --- |
| Say yes to small, no to big | credits ~90%, reserves ~78%, bonds 55–58% | Confidence ↑ · capital ↓ |
| Build budgets to the bone | default ≈ proposal | Lean & trusted ↑ · flexibility ↓ |
| Defer big capital | no facility reserve; facility stuck | Taxes held now ↑ · deficit later ↓ |
| Hold the tax line | rate restraint for years | Confidence ↑ — until the deficits show, then ↓ |

C.  What we would do differently — and why

| Today leads with… | We'd lead with… | Why | First step |
| --- | --- | --- | --- |
| “No” to debt | Save first + leverage aid | Majority vote, not 3/5; unlocks capital | Reserve ladder (Q2) |
| Lean annual budgets | A published 6-year CIP | Surprises become expectations; smooths the rate | CIP drafted (Q1) |
| One-off bond asks | Majority-vote reserves | Clears the 3/5 wall the town keeps hitting | Warrant articles (Q2) |
| Tax-rate headlines | Bill + value transparency | Defuses revaluation confusion | One-page explainer (Q1) |
| Reacting to turnover | Administrator continuity compact | Protects every other initiative | Multi-year TA agreement (Q1) |
| Case-by-case land use | Criteria-based decisions on the record | Cuts litigation exposure (Avanru) | Counsel at hearings |

D.  Financing the backlog — the math that makes it safe

| Lever | Effect |
| --- | --- |
| Stack outside money first | State bridge aid (80%, RSA 234), DWSRF water repaid by rates, CDBG/road aid → ~62% of a ~$5.3M backlog is NON-property-tax money |
| Reserves, not bonds | Local share (~$2.0M) saved via simple-majority reserves — $0 new bonds, no 3/5 votes |
| Phase it | Net-new impact peaks ≈ +$75/yr on a $300K home, then drops BELOW today once built |

E.  Twelve-month plan

| Quarter | Moves |
| --- | --- |
| Q1 | Stabilize the administrator (multi-year agreement + evaluation) · publish a draft 6-year CIP · issue the tax-bill explainer |
| Q2 | Pass the capital reserve ladder (majority votes) · file State Bridge Aid for Christian Hill Rd · commission the water rate study |
| Q3 | Advance DWSRF water financing · deliver one visible 'small win' (ADA via CDBG + reserve) · adopt 5-member board norms |
| Q4 | Bring the full CIP + reserve plan to the deliberative session with an info night · report the year's progress publicly |

The ask: Endorse one principle — keep the restraint, change the instrument — and direct staff to (1) stabilize the administrator, (2) stand up the reserve ladder and a published CIP, and (3) pursue bridge aid and DWSRF for the big items. No new bonds. No tax spike.

Real figures from the Town of Swanzey's own annual reports (2011–2025), NH DRA, and local news; capital figures and forecasts are planning estimates. Companion: full Strategic Review (v0.1), financial model, and capital plan.