## 00 Dashboard
Michigan LTC Network — Resource Recovery Corridor · VAULT Workbook
Control surface. Original files stay preserved · this workbook controls the record · deliverables come from the record. Date 2026-06-05.
Corridor Name | Michigan LTC Network — Resource Recovery Corridor
Public Description | One corridor converting waste streams into recoverable fuel and industrial outputs
Active Sites | Lincoln (Alcona) · Coleman (Midland) · Flint (Genesee)
Lead Applicant | Energy Mann & Sunn, Inc. DBA Michigan LTC
Project Executive | Garrett Schopp (EGLE portal contact)
Operations Lead | Robert C. McCall Jr.
Developer / Financial | Glen D. Scharer / Carbon Alliance Group
Technology | WasteWerx LLC (licensed; IP retained by WasteWerx)
Governance / Compliance | PublicLogic LLC (not a placement agent; fixed/non-contingent fee)
Current Phase | Phase 1 — Discovery & Systems Mapping
Current Priority | Reconcile staffing & financial model; resolve carbon-black + RFS/45Z; EGLE path
Headline economics | Signed Pro Forma EBITDA $30,200,531 (5-FTE basis); operator-reality ~$22,047,043; base-fuel-only floor ~$1,618,483
Current Risk | Staffing (5 vs 62 FTE), feedstock swing, RFS/45Z contingency ($20.4M), securities, source consistency
Next Deliverables | VAULT workbook · proforma reconciliation · grant map · investor/partner packet · data-room index

## 01 Source Register
01 — Source Register
Most important tab. If a number, claim, role, cost, site fact, or public sentence matters, it points to a Source ID.
Source ID | File Name | Folder Path | Type | Date | From | Status | Used In | Notes
SRC-001 | Canonical_Financial_Model v2.0.xlsx | 04_FINANCE/01_Original_Models | Financial model | 2026-05 | Glen / PL | ACTIVE — basis of record | Revenue, P&L, Corridor | Keyed line-for-line to executed WasteWerx Model 3 Pro Forma
SRC-002 | Financial_Reconciliation_Workbook.xlsx | 04_FINANCE/02_Reconciled_Models | Reconciliation | 2026-05 | PL | ACTIVE | Discrepancy log, WasteWerx cost inputs | 3 sources -> one truth; 8 critical discrepancies
SRC-003 | Governance_Workbook.xlsx | 00_CONTROL | Governance | 2026-05 | PL | ACTIVE | VAULT / control | Deal dashboard + VAULT exposure
SRC-004 | Investor_Brief.docx (EM&S deck) | 08_PUBLIC_LANGUAGE/02_Public_Brief | Investor deck | 2026-05 | EM&S / PL | SUPERSEDED (economics) | Narrative / partners | Uses old $16.875M oil+CB model; credits excluded — superseded by SRC-001
SRC-005 | WasteWerx Staffing Proforma.xlsx | 04_FINANCE/04_Staffing_Proforma | Proforma | 2026-05-27 | Vinny Tizio / WasteWerx | NEEDS RECONCILIATION | Staffing model | 62 FTE worst-case 'overkill'; cross-train reduces; MI rates + benefits pending
SRC-006 | EGLE Challenge #4 Application (EQP1168) | 03_GRANTS/01_EGLE/00_Guidance | Grant guidance | 2026-06-02 | EGLE | ACTIVE | Full application | Due 7/7/2026; planning-only; no equipment
SRC-007 | EGLE Challenge #4 Scoring Rubric | 03_GRANTS/01_EGLE/00_Guidance | Grant guidance | 2026 | EGLE | ACTIVE | Application strategy | Emissions 30% / Facility 20% / Community 15% / Tech 15% / Replicability 10% / Team 10%
SRC-008 | EGLE Challenge #4 LOI Feedback | 03_GRANTS/01_EGLE/00_Guidance | Grant guidance | 2026 | EGLE | ACTIVE | Pivot analysis | Carbon-credit research INELIGIBLE; >=50% facility decarb; process change focus
SRC-009 | MI_LTC_LOI_PreFill_FINAL | 03_GRANTS/01_EGLE/01_PreFill | LOI pre-fill | 2026-05-19 | Garrett / PL | SUBMITTED | 3 LOIs | Lincoln/Flint/Coleman; $420k/site
SRC-010 | Lincoln Site Brief / EGLE Project D | 02_SITES/01_Lincoln | Site brief | 2026-05 | PL / team | ACTIVE | Lincoln LOI | National Energy of Lincoln 18 MW biomass; PPA exp 2027
SRC-011 | Coleman Site Brief / CM Rubber | 02_SITES/02_Coleman | Site brief | 2026-05 | PL / team | ACTIVE | Coleman LOI | Geocycle / CM Rubber; Part 169; confirm naming
SRC-012 | Flint Site Brief / Dort Highway | 02_SITES/03_Flint | Site brief | 2026-05 | PL / team | ACTIVE | Flint LOI | ERR; EJ community; brownfield
SRC-013 | LOS_Michigan_LTC_Network_Final.docx | 07_PARTNERS_AND_ROLES/01_Role_Map | Support letter | 2026-05 | Coalition | ON FILE | Grant / partner packet | Joint letter of support
SRC-014 | WasteWerx Mutual NDA (executed) | 11_LEGAL_AND_ENTITY/05_NDAs | NDA | 2026-05-18 | WasteWerx / PL | EXECUTED | IP protection | Protect WasteWerx proprietary tech
SRC-015 | Geocycle Letter of Support | 07_PARTNERS_AND_ROLES/06_Geocycle | Support letter | 2026-01-26 | Paolo Carollo | ON FILE | NextCycle / corridor | Coleman co-location support
SRC-016 | University of Arizona Support (Dr. Cuello) | 07_PARTNERS_AND_ROLES | Support letter | 2026-02-10 | Dr. Joel Cuello | ON FILE | Community / workforce | ACS aquaponic programming
SRC-017 | Acadia Capital validation (Walton) | 04_FINANCE/09_Investor_Readiness | Advisory validation | 2026-05-08 | Brien Walton | ON FILE | Investor readiness | Named governance the critical success factor
SRC-018 | ERR Feedstock Supply (Dort Hwy) | 02_SITES/03_Flint/Source | Supply terms | 2026-05 | ERR Inc. | ON FILE | Feedstock / finance | 10-yr, 40,000 t/yr at $25/ton tipping
SRC-019 | WasteWerx Brochure (IP-Protected) | 07_PARTNERS_AND_ROLES/05_WasteWerx | Technology brochure | 2026 | WasteWerx | ON FILE — CONFIDENTIAL | Technology / partner packet | IP-protected version; partner-facing only; do NOT publish proprietary specs/reactor photos (NDA 5/18)

## 02 Entity + Role Map
02 — Entity + Role Map
Role | Person / Entity | Function | Authority | Public Facing? | Notes
Applicant of Record | Energy Mann & Sunn, Inc. DBA Michigan LTC | Grant applicant / project vehicle | Legal / grant | Yes | LOI submissions
Project Executive | Garrett Schopp | EGLE-facing lead / National Salvage | Operational / external | Yes | Portal contact
Operations Lead | Robert C. McCall Jr. | Corridor operations / EM&S principal | Operational | Yes | EM&S signatory
Developer / Financial | Glen D. Scharer / Carbon Alliance Group | Financial development / capital structure | Strategic | Maybe | Keep clean publicly
Technology Provider | WasteWerx LLC (JT Clark, V. Tizio, E. Rodriguez) | Pyrolysis system (licensed) / proforma source | Technical | Yes | IP retained by WasteWerx; validate assumptions
Governance / Compliance | PublicLogic LLC (Boudreau, Rothschild) | Governance, documentation, grant-stacking, continuity | Advisory | Yes | NOT placement agent; fixed/non-contingent fee
Legal Agent | Michael J. Smith | Registered / legal agent | Legal | Limited | Entity records
Facility Partner | Geocycle / CM Rubber Recycling (Paolo Carollo) | Coleman site context | Site partner | Yes | Part 169; confirm exact language
Facility Partner | Environmental Rubber Recycling (ERR) | Flint site context + feedstock | Site partner | Yes | 10-yr, 40k t/yr, $25/ton tipping
Facility Partner | National Energy of Lincoln LLC | Lincoln site context | Site partner | Yes | 18 MW biomass; PPA exp 2027
Strategic Partner | National Salvage & Service Corp. | Lead applicant affiliate / feedstock | Strategic | Yes | Garrett affiliation; McBain/Lincoln biomass
Capital Advisory | Acadia Capital Management (Brien Walton) | Investment-readiness validation | Advisory | Maybe | Not committed financing

## 03 Site Register
03 — Site Register
Keep removed sites in the register (inactive), never delete — preserves institutional memory.
Site ID | Site | County | Facility / Partner | Feedstock | Status | Grant Use | Notes
SITE-001 | Lincoln | Alcona | National Energy of Lincoln LLC (18 MW biomass) | Tires / biomass / railroad ties (TBD) | ACTIVE | Feasibility / corridor | First LOI priority; PPA exp 2027; ~21 jobs
SITE-002 | Coleman | Midland | Geocycle / CM Rubber Recycling | Tires / industrial material (TBD) | ACTIVE | Feasibility / corridor | Part 169; naming must be consistent
SITE-003 | Flint | Genesee | Environmental Rubber Recycling (Dort Hwy) | Tire / rubber stream | ACTIVE | Feasibility / corridor | EJ community; ERR role needs clean language
SITE-004 | Coldwater | Genesee (Genesee Twp) | RACER #13270 (TBD) | TBD | INACTIVE / Phase 2 | None | Do not reintroduce unless revived; keep for memory

## 04 Grant Register
04 — Grant Register
Grant ID | Program | Agency | Status | Ask | Match | Site(s) | Deadline | Lead | Notes
GRANT-001 | MI Healthy Climate Challenge #4 — Go Big, Go Clean | EGLE | LOIs submitted; full app due 7/7 | $420,000/site; $1,260,000 total | TBD | Lincoln, Coleman, Flint | Full app 7/7/2026 | Garrett | Planning-only; carbon credits ineligible; needs >=50% facility decarb framing
GRANT-002 | Scrap Tire Market Development Grant | EGLE / Michigan | Future target | TBD | ~50% cost share | TBD | FY27 | TBD | Equipment funding path (this one CAN fund equipment)
GRANT-003 | USDA REAP / B&I | USDA | Research | Up to $1M grant / $25M guarantee | TBD | Coleman (rural) | TBD | TBD | Rural facility path
GRANT-004 | EPA Brownfield Cleanup & Assessment | EPA | Research | $500K-$2M | 20% (waivable) | Flint / Dort | TBD | TBD | Brownfield reuse
GRANT-005 | EDA Public Works / NextCycle MI | EDA / MI | Research | Up to $3M / $50-250K | TBD | Corridor | NextCycle applied Mar 2026 | TBD | Future stack

## 05 Financial Assumptions
05 — Financial Assumptions (keyed to Canonical v2.0)
Separates confirmed numbers / contingent credits / stress assumptions / open items. Keeps the model from becoming mythology.
ID | Item | Value | Source | Status | Notes
FIN-001 | Total revenue (Pro Forma) | $35,581,680 | SRC-001 | CONFIRMED | Fuel + RIN + 45Z
FIN-002 | Base fuel (RD $4,798,080 + SAF $10,355,040) | $15,153,120 | SRC-001 | CONFIRMED | Sells on contract/market
FIN-003 | RIN + Section 45Z credits | $20,428,560 | SRC-001 | CONTINGENT | Flag 3: requires EPA RFS registration — not guaranteed
FIN-004 | Carbon black | $0 (base) | SRC-001 | OPEN — Flag 1 | Not in executed Pro Forma; deck implied ~$10.125M; uncontracted
FIN-005 | Opex — Pro Forma (as signed, 4 FTE + manager) | $5,381,149 | SRC-001 | AS SIGNED | Labor only $425,000 — see staffing tension
FIN-006 | Opex — operator reality (62-FTE staffing + feedstock) | ~$13,534,637 | SRC-001/SRC-005 | STRESS | Delta ~$8.15M vs Pro Forma
FIN-007 | EBITDA — signed (PF opex) | $30,200,531 | SRC-001 | AS SIGNED | Rests on a 5-person crew
FIN-008 | EBITDA — operator reality (fuel+credits) | ~$22,047,043 | Derived | DILIGENCE REALITY | Real staffing + feedstock
FIN-009 | EBITDA — base fuel only @ operator opex | ~$1,618,483 | Derived | FLOOR | Without credits, barely breakeven
FIN-010 | Year 1 cash out | $7,622,828 | SRC-001 | CONFIRMED | WasteWerx $6,670,328 + capex $952,500
FIN-011 | WasteWerx license fee | $5,500,000 | SRC-001/002 | CONFIRMED | Net of $50k design credit; NOT depreciable
FIN-012 | Production royalty | $0.60/gallon | SRC-001 | CONFIRMED | IoT-metered
FIN-013 | Monthly monitoring | $35,000/month | SRC-001 | CONFIRMED | CPI-indexed, from commissioning
FIN-014 | MAR | Yr1 70% / Yr2+ 80% | SRC-002 | CONFIRMED | Of nameplate royalty
FIN-015 | Staffing (worst-case) | 62 FTE / $5,522,400 | SRC-005 | NEEDS RECONCILIATION | Vincent: worst-case; MI rates + cross-training + benefits pending
FIN-016 | Feedstock swing | $940k PF / $3.72M deck / ~$1M ERR tipping | SRC-001/002/018 | OPEN | ERR $25/ton tipping would lower opex
FIN-017 | Simple payback | ~0.25 yr | SRC-001 | EXPLAIN | On signed basis; aggressive — caveat required
FIN-018 | Community profit share | 10% of EBITDA | SRC-001 | CONFIRMED | Contractual, locally directed

## 06 Staffing + Operations
06 — Staffing + Operations (the diligence swing)
Two WasteWerx documents conflict on staffing. Resolve actual headcount (cross-trained middle) before investor numbers.
ID | Role | Pro Forma (signed) | Staffing Proforma (worst-case) | Status | Notes
OPS-000 | TOTAL LABOR | 4 FTE + manager = $425,000 | 62 FTE = $5,522,400 (FL) | OPEN | The single biggest swing in the model
OPS-001 | Plant Manager | incl. in $425k | 1 FTE | Open | Confirm per site
OPS-002 | Operating labor / operators | 4 FTE | ~16-30 FTE (24/7 x 4 shifts) | Open | Staffing ratio drives everything
OPS-003 | Maintenance & reliability | — | ~8 FTE | Open | Shared vs per-site
OPS-004 | Feedstock / yard / logistics | — | ~11 FTE | Open | Biomass moisture mgmt = full-shift
OPS-005 | Fuel processing & carbon co-product | — | ~14 FTE | Open | Distillation + carbon handling
OPS-006 | QA/lab, HSE, MRV, admin | — | ~13 FTE | Open | MRV analyst from Day 1
OPS-007 | Benefits / burden | not detailed | 30% burden assumed | Open | Vincent: health insurance needs actuals

## 07 Regulatory Register
07 — Regulatory Register
Reg ID | Agency | Item | Site | Status | Owner | Notes
REG-001 | EGLE | Pre-application transmittal | Corridor | Sent / pending | Garrett / PL | Sent to Nicole Sanabria
REG-002 | EGLE | LOI confirmation | Lincoln | Submitted | Garrett | Confirmation requested (no auto-email)
REG-003 | EGLE | LOI confirmation | Coleman | Submitted | Garrett | Same
REG-004 | EGLE | LOI confirmation | Flint | Submitted | Garrett | Same
REG-005 | EGLE | Air PTI / NSR / Title V applicability | Each site | Open | TBD | Map by site; WasteWerx low-filtration claim helps
REG-006 | EGLE | Part 169 scrap tire / solid waste | Each site | Open | Operator | Material-specific
REG-007 | Local | Site / zoning approvals | Each site | Open | Site partner | Unknown
REG-008 | Federal/Tax | RFS pathway petition + 45Z qualification | Corridor | Open — Phase 1 | Glen / counsel | Gates $20.4M of revenue (FIN-003)

## 08 Decision Log
08 — Decision Log
Decision ID | Date | Decision | Made By | Evidence | Affected Outputs | Notes
DEC-001 | 2026-05 | Corridor framing instead of replication | PL / team | Draft history | Website, grants, briefs | 'Replication' removed
DEC-002 | 2026-05 | One corridor publicly; no hard site count in hero | PL / team | Website canon | Public copy | Internal count remains 3
DEC-003 | 2026-05-19 | Submit three separate LOIs | Garrett / PL / team | LOI package | EGLE submissions | Risk noted (RISK-006)
DEC-004 | 2026-05 | $420,000 per site ask | Team | LOI pre-fill | EGLE LOIs | Total $1,260,000 (note: <$400k encouraged)
DEC-005 | 2026-05 | Exclude Coldwater from active package | Team | Site register | Grants / website | Keep inactive (SITE-004)
DEC-006 | 2026-05 | Garrett = portal contact | Team | LOI pre-fill | EGLE portal | EM&S remains applicant
DEC-007 | 2026-06 | Canonical v2.0 = single source of truth for economics | PL | SRC-001 | Model / investor | Supersedes EM&S deck economics (SRC-004)
DEC-008 | 2026-06 | Anchor investor headline on base + labeled contingent upside | PL | Reconciliation | Investor deck | Do not lead with $30.2M alone

## 09 Open Questions
09 — Open Questions (be brutally honest)
Q ID | Question | Category | Owner | Status | Needed Source
Q-001 | Actual Michigan staffing: 5 (Pro Forma), 62 (staffing), or cross-trained middle? | Staffing | Robert / Vinny / Glen | OPEN | Reconciled staffing proforma
Q-002 | Are insurance/benefits actuals included in staffing burden? | Finance | Glen / Robert | OPEN | Insurance + benefits quote
Q-003 | Is carbon black additive to distilled fuel, and at what grade/price? | Finance | Glen / WasteWerx | OPEN | Feedstock yield model + offtake
Q-004 | RFS registration + 45Z qualification timeline? | Regulatory/Tax | Glen / counsel | OPEN — Phase 1 | RFS petition + 3rd-party engineering
Q-005 | Feedstock: $0.20/gal, $200/ton, or $25/ton ERR tipping? | Finance | Robert / ERR | OPEN | ERR supply agreement
Q-006 | Equipment / depolymerization cost by site? | Finance/Grant | WasteWerx / Glen | OPEN | Vendor quote
Q-007 | Which investor return structure ($3.5M/4yr vs $5M/5yr+balloon)? | Finance/Legal | Team / counsel | OPEN — CRITICAL | Securities counsel
Q-008 | Parent holdco legal name + SPV chart + LARA registration? | Legal/Entity | Robert / counsel | OPEN | Entity formation docs
Q-009 | Public role each facility partner approves? | Public language | PL / Garrett | OPEN | Partner approval

## 10 Claims + Evidence
10 — Claims + Evidence (public-safety tab)
How you avoid accidental overclaiming. Banned claims stay listed.
Claim ID | Claim | Use Case | Public Safe? | Source | Status
CLAIM-001 | Michigan LTC is a resource recovery corridor | Website / grant | Yes | Corridor brief | Approved
CLAIM-002 | Corridor includes Lincoln, Coleman, and Flint | Internal / grant | Conditional | Site briefs | Avoid hard count in hero
CLAIM-003 | Converts waste into fuel + co-products (licensed pyrolysis) | Grant / technical | Yes if sourced | WasteWerx (NDA) | Exact wording; no proprietary specs/images
CLAIM-004 | Steady-state EBITDA $30.2M | Investor / internal | NOT public without context | Canonical (SRC-001) | Caveat: 5-FTE basis; operator-reality ~$22M
CLAIM-005 | Payback ~3 months | Internal | Sensitive | Canonical | High scrutiny; requires caveat
CLAIM-006 | $35.58M revenue | Investor | Conditional | Canonical | $20.4M is RFS-contingent — label as upside
CLAIM-007 | Fully permitted | Any | NO — BANNED | None | Do not use unless true
CLAIM-008 | Zero-emission | Any | NO — BANNED | None | Do not use unless proven
CLAIM-009 | Carbon black revenue | Investor | NO without contract | None (Flag 1) | $0 in executed pro forma
CLAIM-010 | Legacy is what the next generation can use | Website / brand | Yes | Canon | Approved — emotional center

## 11 Deliverables Register
11 — Deliverables Register
Del ID | Deliverable | Audience | Status | Owner | Notes
DEL-001 | EGLE LOI — Lincoln/Coleman/Flint | EGLE | Submitted 5/19 | Garrett / PL | Three separate LOIs
DEL-002 | EGLE Challenge #4 Lincoln Full Application (draft) | EGLE | Draft | PL | Pivoted to facility-decarb; due 7/7
DEL-003 | Canonical Financial Model (reconciled) | Internal / investor | Current | PL / Glen | SRC-001 basis; base vs operator-reality
DEL-004 | Headline Economics Memo (McCall/Scharer) | Internal | Current | PL | Base vs contingent; what to prove
DEL-005 | VAULT Assessment + Register | Internal / partners | Current | PL | 5 pillars; readiness rollup
DEL-006 | Path-to-All-A + Investment-Grade Scorecard | Internal | Current | PL | C+ -> A roadmap
DEL-007 | Investor Deck Prompt + draft package | Internal | Draft | PL | Securities + IP guardrails baked in
DEL-008 | Staffing Reconciliation Brief | Glen / Robert | Planned | PL | Michigan rates + cross-training
DEL-009 | Data-Room Index | Investor / partners | Planned | PL | Catalog financials + support letters (this workbook's companion)
DEL-010 | Corridor Partner Packet | Partners / funders | Planned | PL | Needs clean role map (tab 02)

## 12 Public Language
12 — Public Language
Item | Approved Phrase | Avoid | Notes
Corridor | Michigan LTC Network — Resource Recovery Corridor | Three-plant rollout (unless context) | Public-facing
Sites | Lincoln, Coleman, and Flint (when needed) | Hard count in hero | Internal count is 3
Technology | Resource recovery using licensed pyrolysis technology | Magic / revolutionary / guaranteed | IP retained by WasteWerx
Climate | Cleaner industrial recovery pathway | Zero-emission (unless proven) | Avoid overclaim
Economics | Model-based project economics (assumptions stated) | Guaranteed returns / unqualified $30.2M | Lead with base; credits as upside
Legacy | Legacy is what the next generation can use | Buzzword sustainability | Emotional center
Public proof | Documentation-first, verification-ready | Trust us | Strong posture
Mantra | Carbon to Capacity. Capital to Community. Continuity for the next generation. | Over-explaining entity structure | Use sparingly

## 13 Risk Register
13 — Risk Register
Risk ID | Risk | Severity | Category | Mitigation | Owner
RISK-001 | Financial model looks too strong without support | High | Finance | Base + sensitivity + source notes (SRC-001) | Glen / PL
RISK-002 | Staffing generic, not Michigan-adjusted (5 vs 62 FTE) | High | Operations | Reconcile proforma (Q-001) | Robert / Vinny
RISK-003 | Public language overclaims readiness | High | Communications | Claims register (tab 10) | PL
RISK-004 | RFS/45Z contingency = $20.4M of revenue | High | Regulatory/Finance | RFS petition Phase 1; label as upside | Glen / counsel
RISK-005 | Securities offering with no Reg D / PPM | High | Legal | Securities counsel; PL not placement agent | Counsel / PL
RISK-006 | Three LOIs vs corridor logic | Medium | Grants | Document rationale (DEC-003) | PL
RISK-007 | Carbon black narrative vs model ($0) | Medium | Finance | Clarify inclusion (Q-003) | Glen
RISK-008 | Partner roles blur across entities | Medium | Governance | Maintain role map (tab 02) | PL / Robert
RISK-009 | WasteWerx IP exposure (licensed) | Medium | Legal/IP | NDA + generic visuals + license disclosure | PL / WasteWerx
RISK-010 | Old site (Coldwater) reappears | Low | Record control | Inactive site register (SITE-004) | PL

## 14 Contact Register
14 — Contact Register
Contact | Entity | Role | Email | Notes
Robert C. McCall Jr. | EM&S | Operations lead / signatory | mccall@acscoop.com | 216-906-2907
Garrett Schopp | National Salvage | Project Executive / EGLE lead | Robert.Mccall@nssccorp.com (portal) | 812-345-2543
Glen D. Scharer | Carbon Alliance Group | Developer / financial | glen@carbonalliance.earth | 863-255-8227
Vincent (Vinny) Tizio II | WasteWerx | Staffing proforma / technology | vinny@wwerx.com | 941-600-3018
Nathan Boudreau | PublicLogic | Governance / documentation | nate@publiclogic.org | 978-807-0829
Dr. Allison Weiss Rothschild | PublicLogic | Org systems / continuity | allie@publiclogic.org | TBD
Michael J. Smith | Legal | Agent / attorney | TBD | Entity
Nicole Sanabria | EGLE | Regulatory contact | TBD | Pre-app transmittal
Haley Neuenfeldt | EGLE | Challenge #4 program contact | NeuenfeldtH@Michigan.gov | LOI / application
Brien Walton | Acadia Capital | Capital advisory | TBD | Validation 5/8/26
Paolo Carollo | Geocycle | Coleman host | TBD | LOS 1/26/26

## 15 Change Log
15 — Change Log (what changed in the record)
Change ID | Date | Item Changed | From | To | Reason
CHG-001 | 2026-05 | Grant ask | $600K/$550K/$500K concepts | $420K/site | Fit total ask
CHG-002 | 2026-05 | Public site count | Hard count | One corridor | Public canon
CHG-003 | 2026-05 | Framing | Replication | Corridor standard | Strategic language
CHG-004 | 2026-05 | Site list | Included Coldwater | Removed Coldwater | Active package narrowed
CHG-005 | 2026-05 | Applicant framing | Partner-specific | EM&S DBA Michigan LTC | Submission consistency
CHG-006 | 2026-06 | Revenue model basis | EM&S deck $16.875M (oil+CB) | Canonical $35.58M (fuel+credits) | Executed Pro Forma
CHG-007 | 2026-06 | Opex treatment | Single $5.38M (5 FTE) | Two-case: PF vs operator-reality (62 FTE) | Staffing tension surfaced
CHG-008 | 2026-06 | Credit portion | ~$13.4M (recon note) | $20,428,560 (canonical line items) | Canonical exact split

## 16 Reuse Library
16 — Reuse Library (the future advantage)
Reuse ID | Asset | Can Reuse For | Status | Notes
REUSE-001 | Corridor description | Grants, website, partner packet | Approved | Keep source-backed
REUSE-002 | Site brief format | Future sites | Approved | Lincoln/Coleman/Flint template
REUSE-003 | EGLE LOI answer pattern | Future grants | Approved | Adapt carefully
REUSE-004 | Role map format | Partner packets | Approved | Prevents confusion
REUSE-005 | Public-safe claims table | Website / PR | Approved | Avoids overclaiming
REUSE-006 | Two-case opex / staffing reconciliation | Other industrial projects | Draft | Needs final proforma
REUSE-007 | Canonical-vs-reality financial structure | Investor memos | Draft | Base + labeled contingent upside
REUSE-008 | VAULT Workbook (this file) | Every corridor / state SPV | Approved | The control surface template