Swanzey Operating Plan

Budget · Forecast · Capital — a consolidated operating reference

PRIVATE working document · v0.1 · June 2026

Built on the Town's own annual reports (2011–2025), NH DRA, and local news

Convert to the live operating plan on hire — figures keyed to town-meeting year

0.  Purpose

One reference that holds the Town's budget, a forecast, and the capital plan together. It is written to be operational: on hire, the forecast cells become the working model, the reserve ladder becomes warrant articles, and the 12-month plan becomes the calendar. Every figure traces to the Town's own annual reports; capital figures and forecasts are clearly-labeled planning estimates.

Operating thesis: the Town will SAVE but won't BORROW. Fund the backlog with majority-vote reserves + state aid + the water revolving fund — not bonds — and the projects that keep stalling get built without a tax spike or a 3/5 vote.

PART I — BUDGET

1.  The 15-year record

Operating budgets have risen ~55% since 2012 to roughly $8.94M (2026), with a flat early-2010s (~+1%/yr) giving way to a +6–7%/yr climb since 2020.

Operating budget by town-meeting year, 2012–2026, with the forecast band (Part II).

| Meeting year | Operating (proposed) | Default | Budget % YES |
| --- | --- | --- | --- |
| 2012 | $5,747,885 | $5,705,757 | 80% |
| 2016 | $6,262,426 | $6,067,144 | 68% |
| 2020 | $6,303,000 | $6,072,735 | — |
| 2023 | $7,425,000 | $7,468,834 | 62% |
| 2025 | $8,370,000 | $7,935,699 | 57% |
| 2026 | $8,939,036 | $8,891,785 | passed |

2.  How the budget works (and why the 'no' lever is gone)

Governing law — RSA 32. Appropriation by purpose; no over-expenditure (32:8); transfers within the total (32:10); lapse at year-end (32:7); emergency over-spend needs DRA approval (32:11).

Forms. MS-636 (proposed) or MS-737 (budget-committee towns, filed within 20 days of the meeting); MS-232 'Appropriations as Voted' filed within 20 days.

SB2 default budget — RSA 40:13, IX. If the operating article fails, the default budget takes effect. In Swanzey the default now sits within ~$47K of the proposal — and exceeded it in 2017, 2018, and 2023. 'Vote no to save' no longer works.

Proposed minus default budget by meeting year — repeatedly near zero or negative.

3.  Cost drivers

The climb is structural, not programmatic: health insurance, wages, the NH Retirement System (RSA 100-A) employer rate, and the ambulance/EMS contract. These are largely non-discretionary, so honesty about them — and relentless capture of outside money — is the only durable lever on the municipal share.

4.  Tax rate & the 2024 revaluation

Total rate moved $24.51 (2021) → $26.87 (2023) → $19.06 (2024) → $20.18 (2025). The 2024 drop was a revaluation (assessed values rose), not a tax cut. Education is ~60% of the bill; the municipal share the Board controls is ~a quarter.

Total tax rate by component, 2021–2025. The 2024 step-down is the revaluation.

PART II — FORECAST

Modeled. Compounds the 2026 adopted budget ($8,939,036) at the observed recent band (low 4.5% / base 6.0% / high 7.5%; recent CAGR ≈ 6.7%). Scenarios, not predictions.

| Fiscal year | Low (4.5%) | Base (6.0%) | High (7.5%) |
| --- | --- | --- | --- |
| 2026 (actual) | $8.94M | $8.94M | $8.94M |
| 2027 | $9.34M | $9.48M | $9.61M |
| 2028 | $9.76M | $10.04M | $10.33M |
| 2029 | $10.20M | $10.65M | $11.10M |
| 2030 | $10.66M | $11.29M | $11.94M |
| 2031 | $11.14M | $11.96M | $12.83M |

Base case crosses $10M around 2028 and approaches $12M by 2031 — with no new services, purely on the cost escalators.

Budget-approval risk

Operating-budget support has slid from ~80% (2011–15) to 57% (2025). On trend a budget failure becomes plausible within a few cycles — though, because the default ≈ the proposal, the fiscal consequence is now muted; the real contest moves to special/capital articles.

Operating-budget support, 2011–2025, with trend.

Fund-balance guidance. Hold unassigned fund balance in DRA's prudent band (≈ 5–17% of the operating budget). Treat any amount 'applied to reduce taxes' as multi-year smoothing, not a one-year cut — over-applying lowers next year's base and spikes the rate.

PART III — CAPITAL PLAN

5.  The backlog and the 3/5 problem

About $5.3M of identified needs: the public-works facility, the Christian Hill Road bridge, Lower Winchester Street, the West Swanzey water system, and Town Hall accessibility. The facility won majorities in 2024 and 2026 but failed the 3/5 a bond requires. Reserves and credits, by contrast, pass 78–90%.

What passes easily versus what dies at the 3/5 wall.

6.  The funding strategy — 62% other people's money

Stack outside funding first: 80% state bridge aid (RSA 234) for the bridge; the DWSRF (repaid by water rates, plus principal forgiveness) for water; block grant and CDBG for the street and ADA work. About 62% of the backlog is non-property-tax money, leaving ~$2.0M local — saved via majority-vote reserves, with $0 new bonds.

Funding stack by project: most cost carried by aid, water rates, and grants.

| Project | Total | Local share | Primary funding path |
| --- | --- | --- | --- |
| Public Works Facility | $1.20M | $1.20M | RSA 35 reserve (pay-go ~2031) |
| Christian Hill Rd Bridge | $1.00M | $0.20M | RSA 234 aid 80% + bridge reserve |
| Lower Winchester St | $0.75M | $0.48M | Highway block grant + roads reserve |
| West Swanzey Water | $2.075M | ~$0 (tax) | DWSRF, repaid by water rates + grants |
| Town Hall ADA | $0.25M | $0.125M | CDBG + facilities reserve |
| TOTAL | $5.275M | $2.005M (38%) | $0 new bonds |

7.  The reserve ladder & the tax glide

| Capital Reserve Fund | Annual deposit | Funds | Vote |
| --- | --- | --- | --- |
| Public Works Facility | $150–300K | the facility | majority |
| Bridges | $50K | Christian Hill 20% | majority |
| Highway Reconstruction | $100K | Lower Winchester St | majority |
| Highway Equipment | $90K | fleet cycle | majority |
| Fire Apparatus | $70K | engine/tanker cycle | majority |
| Town Facilities (ADA) | $40K | Town Hall, buildings | majority |
| Technology & Records | $20K | GIS, cyber, retention | majority |

Net-new tax impact on a $300,000 home: peaks ≈ +$75, then below today once built.

8.  Decision rules

| If the project is… | Use… | Because |
| --- | --- | --- |
| ≤ ~$250K, recurring | a capital reserve (pay-go) | simple majority, no interest |
| a town bridge (≥10 ft) | RSA 234 aid + reserve for 20% | state pays 80% |
| water/sewer | DWSRF, repaid by rates | off the property tax |
| large, urgent, unavoidable | Bond Bank (RSA 33) — last resort | only when reserves can't get there in time |
| anything | listed in the published CIP first | surprise becomes expectation |

DRA-compliant model warrant articles for the reserve ladder and the bridge-aid / DWSRF / CDBG authorizations are ready in the companion capital-forecast folder.

PART IV — OPERATING PLAYBOOK

9.  The first twelve months

| Quarter | Moves |
| --- | --- |
| Q1 | Stabilize the administrator's office (multi-year agreement + written evaluation). Publish a draft six-year CIP. Issue the one-page tax-bill explainer. |
| Q2 | Warrant & pass the capital reserve ladder (majority votes). File State Bridge Aid for Christian Hill Rd. Commission the water rate study. |
| Q3 | Advance DWSRF water financing. Deliver one visible 'small win' (ADA via CDBG + reserve). Adopt operating norms for the five-member board. |
| Q4 | Bring the full CIP + reserve plan to the deliberative session with an information night. Report the year's progress publicly. |

10.  The annual municipal cycle

| When | What |
| --- | --- |
| By Sept 1 | File MS-1 (valuation), MS-434 (revenues), MS-535 (financial report) |
| Oct–Dec | Build budget & default budget; CIP update; budget public hearing; post warrant (RSA 31:95) |
| ~1st Tue Feb | SB2 deliberative session (debate & amend) |
| ~2nd Tue Mar | SB2 ballot: budget, articles, officer elections |
| Meeting +20 days | File MS-232 'Appropriations as Voted' |
| Fall | DRA sets the tax rate; issue tax bills |

11.  Dashboard — the numbers to watch

| Metric | Watch |
| --- | --- |
| Operating budget / YoY | ~$8.94M; keep YoY honest about drivers |
| Budget % YES | 57% (2025) — arrest the slide with transparency |
| Unassigned fund balance | keep within ~5–17% of operating budget |
| Reserve balances | grow toward project targets (ladder above) |
| Next statutory deadline | always know it (MS-1 / MS-232 / hearing / warrant) |
| Tax rate & valuation | total $20.18 (2025); refresh real MS-1 valuation |

Appendix — Provenance & key RSA

Real figures from the Town of Swanzey's annual reports (2011–2025), NH DRA, and local news; capital figures and forecasts are clearly-labeled planning estimates, keyed to town-meeting year (verified against as-voted results for 2020/2023/2025). Key statutes: RSA 32 (budget), 40:13 (SB2/default), 35 (reserves), 33/35-A (bonding/Bond Bank), 234 (bridge aid), 38 (utilities), 162-K (TIF), 674:5-8 (CIP), 91-A (right-to-know), 33-A (records), 165 (welfare), 273-A (labor), 100-A (NHRS). Companion files: Financial Review, Capital Workbook (live model), Strategic Review, and the Interview Workbook.