## Overview
EM&S MICHIGAN LTC NETWORK — GOVERNANCE COMPLIANCE WORKBOOK
PublicLogic LLC • May 2026 • Confidential
| Developer | Energy Mann & Sunn, Inc. (McCall, Schopp, Smith)
| Technology Partner | WasteWerx LLC
| Project Coordinator | Carbon Alliance Group (Glen Scharer)
| Feedstock Partners | National Salvage & Service Corp.; E.R.R. Inc.; Geocycle LLC
| Governance | PublicLogic LLC
| Community Partners | The Warehouse / Gen 215; ACS Cooperative
| Advisory | Acadia Capital Management (Brien Walton)
| Sites | Coldwater Road (118.3ac); Dort Highway (14ac); Coleman (co-location)
| Dev Cost (Deck) | $12,200,000 per site
| Updated Budget | ~$15,000,000 per site
| Annual Revenue | $16,875,000 per site
| Investor Equity | 30% available
| Community Allocation | 10% to nonprofits

## Site Budgets
DEVELOPMENT COSTS — PER EM&S DECK
| Cost Category | Deck Amount | Notes
| Licensing + Permits | 120000
| A/E Fees | 500000
| Security + Data Infrastructure | 400000
| Site Work + Utilities | 800000 | 20K SF @ $40
| Building w/ Fire Suppression | 4500000 | 20K SF @ $225
| Depolymerization Plant (2 units) | 4600000 | WasteWerx @ $2.3M ea
| Diesel Storage Tank (30K gal) | 192000
| Shipping + Freight | 100000
| Customs + Duty | 35000
| Commissioning | 50000
| Training + Support | 65000
| Forklifts (2) | 41200
| Contingency (8%) | 800000
TOTAL

## VAULT Findings
VAULT ASSESSMENT — PRIORITY ACTION ITEMS
| Pillar | Finding | Priority | Action Required
| V | Financial model: 3 conflicting versions | CRITICAL | Author single proforma
| V | Revenue distribution: 45.5% unallocated | HIGH | Define before investor comms
| V | Investor return: two different structures | HIGH | Resolve; engage securities counsel
| A | No EM&S operating agreement | CRITICAL | Draft before RACER purchase
| A | LARA registration unconfirmed | CRITICAL | MiBusiness Registry lookup now
| A | SPV may not be formed | HIGH | File MI formation documents
| A | Dort Highway agreement unsigned | HIGH | Execute; complete blank exhibits
| U | No permit register exists | CRITICAL | Stand up compliance tracking immediately
| U | Off-take contracts not exhibited | HIGH | Obtain and document
| U | Community 10% is verbal only | MEDIUM | Encode in operating agreements
| L | Restrictive covenant not reviewed | HIGH | Confirm pyrolysis permitted
| L | Tax treatment unusual (6% on gross) | MEDIUM | Tax counsel review
| T | All knowledge in McCall relationships | CRITICAL | System must capture institutional knowledge for 25-year term
| T | No succession protocol | HIGH | Document in operating agreement

## Milestones
COMPLIANCE & PERMITTING MILESTONES
| Phase | Milestone | Responsible | Target | Status
| Ph 1 | Partnership agreements established | PublicLogic/Glen | May 2026 | Carbon Alliance + WasteWerx
| Ph 1 | LARA registration confirmed | EM&S | May 2026 | Pending
| Ph 1 | Proforma reconciliation | EM&S/CA | May 2026 | Pending
| Ph 1 | VAULT briefing delivered | PublicLogic | May 2026 | Complete
| Ph 1 | Cover letters finalized | PublicLogic | May 2026 | Complete
| Ph 1 | Restrictive covenant review | PublicLogic | Jun 2026 | Not Started
| Ph 1 | Dort Hwy agreement executed | EM&S/All | Jun 2026 | Not Started
| Ph 2 | EGLE pre-app meeting | PublicLogic/EM&S | Jun 2026 | Not Started
| Ph 2 | RACER acquisition (Coldwater) | EM&S | Jul 2026 | Not Started
| Ph 2 | BEA filed | PublicLogic | Jul 2026 | Not Started
| Ph 2 | Securities counsel engaged | EM&S | Jul 2026 | Not Started
| Ph 2 | SPV formations | EM&S/Legal | Jul 2026 | Not Started
| Ph 3 | Air PTI application | PublicLogic/A&E | Sep 2026 | Not Started
| Ph 3 | Part 169 registration | PublicLogic | Jan 2027 | Not Started
| Ph 3 | NextCycle MI decision | EGLE | Summer 2026 | Waiting